## 1st overarching objective GEP
EIT Gender Equality Action Plan 2025-2027
1st Overarching objective: Strengthening the role of the EIT in the European innovation landscape in promoting gender equality
Thematic area | Objective | Activity | Results Indicators | Responsible(s) | Timeline
Innovation | 1. Increase participation of women in the EIT KICs innovation programmes to 30% | Introduce gender-balanced teams, including at the decision-making level, as a recommendation in EIT KICs Innovation Calls for Proposals. | EIT KICs Innovation Calls for Proposals include as a recommendation gender-balanced teams at all levels. | EIT KICs - implementation and reporting EIT OPS1, external experts - Calls monitoring and evaluation | Annually
|  | Improve/introduce strategies and measures to increase participation of women in innovation programmes. Possible measures examples include: Active outreach to and recruitment of women innovators, through tailored communication channels, and targeted marketing activities. Gender bias/ Diversity & inclusion/gendered innovation trainings for selection panels, innovation leads, advisory boards, expert groups and supported start-ups. Gender-balance in selection panels, evaluation committees, advisory boards. Inclusive innovation programmes design - taking into consideration, in relevance with the KICs business strategy, broader diversity dimensions, intersectionality. Gender-budgeting. Setting-up sector/KIC relevant KPIs/targets for the percentage of budget dedicated to support women innovators. Monitor and report on it. | EIT KICs have quality strategies and Action Plan in place, with sector-relevant KPIs and targets, to increase participation of women in innovation programmes. The Action Plan is monitored and annually reported on. 30% of EIT KICs start-ups created off/for innovation have woman CEO/Owner [KPI EITHE04.1/gender] by December 2027 | EIT KICs - implementation and reporting (Annual Gender Mainstreaming Report on Strategies and actions/measures implemented to ensure gender balance and incorporation of gender dimension in the EIT KICs innovation, business creation, education programmes, and results of these actions. (GMR) KPI reporting [EITHE04.1/gender] EIT IES Gender Equality Lead, IES Innovation Lead - GMR assessment and steering exchange of knowledge and good practices EIT OPS1 - KPIs/gender | Annually. Participation target to be reached by 2027
| 2. Ensure that EIT KICs-supported innovations, unless specified otherwise in the topic description, incorporate gender dimension | Incorporate gender dimension into EIT KICs Innovation Calls for Proposals as obligatory, award criterion, unless specified otherwise in the topic description. Where relevant, include intersectionality, diversity & inclusion. | KIC Innovation Calls for Proposals, unless specified otherwise in the topic description, include incorporation of gender dimension as an obligatory/Award criterion. | EIT KICs - implementation and reporting EIT OPS1, external experts - Calls monitoring and evaluation | Annually as of 2026
|  | Monitor and report on KIC most impactful good practices and success stories on increasing participation of women, and bringing gendered innovation to the market, including on the KIC- supported collaborative innovation projects, focusing on women and/or FemTech topic areas and/or conditions disproportionately impacting women. | Annual EIT KICs Gender Mainstreaming Report includes information on the most impactful good practices and success stories on increasing participation of women and bringing gendered innovation to the market. Key figures and selected good practices are included in the "EIT KICs Impactful Innovation guide". | EIT KICs - Implementation and reporting EIT IES Gender Equality Lead, Innovation Lead - GMR assessment and steering exchange of good practices | Annually
Business Creation & Acceleration | 3. Increase participation of women in EIT KICs business creation and acceleration programmes to 35% | Introduce gender mainstreaming, inclusive programmes design, as an award criterion in EIT KICs Business Creation and Acceleration Calls for Proposals. | EIT KICs Business Creation & Acceleration Calls for Proposals include gender mainstreaming, inclusive programme design, as an award criterion. | EIT KICs - implementation and reporting EIT OPS1, external experts - Calls monitoring and evaluation | Annually, as of 2026
|  | Improve/introduce strategies and measures to ensure gender-smart approach to investment. Possible measures examples include: At scouting phase active outreach to women-led startups. Gender-balanced and gender-bias/gender mainstreaming trained investment committee. During the selection: higher scoring for women-led, gender-balanced start-ups on the "team" criterion. Throughout this process, collection of gender-disaggregated data, tracking and reporting progress. | EIT KICs have quality strategies and Action Plan in place, with sector-relevant KPIs and targets, to ensure gender smart approach to investment. The Action Plan is monitored and annually reported on. 35% of the EIT KICs supported start-ups and scale-ups have woman CEO/Owner [KPI EITHE03.1/gender] | EIT KICs - implementation and reporting (GMR); KPI reporting [EITHE03.1/gender] EIT IES Gender Equality Lead, Business Creation & Acceleration Lead: assessment and steering exchange of knowledge and good practices OPS1: KPIs/ gender | Annually. Participation target to be reached by 2027
|  | Strengthened and expend the EIT Community SUPERNOVAS programme to bridge gender gaps in entrepreneurship and investment. | SUPERNOVAS Women Investor Network has minimum 400 Members by 2027. Minimum 800 women undergo SUPERNOVAS investment and entrepreneurship trainings by 2027. | EIT KICs participating in SUPERNOVAS: implementation EIT IES Cross-KIC Officer - steering and monitoring | Annually, target by 2027
|  | Monitor and report on KIC impactful good practices and success stories on increasing participation of women, gender-smart investment, and inclusive Business creation & acceleration programme design- taking into consideration, in relevance with KIC business strategy, broader diversity dimensions, intersectionality. | Annual EIT KICs Gender Mainstreaming Report, includes information on impactful good practices and success stories on gender mainstreaming, inclusive programme design, in EIT KICs Business Creation and Acceleration Programmes. Key figures and selected good practices are included in the "EIT KICs Impactful BC guide". | EIT KICs - Implementation and reporting (GMR) EIT IES Gender Equality Lead, Business Creation & Acceleration Lead - GMR assessment and steering exchange of good practices | Annually
Education | 4. Ensure gender-balanced participation in EIT KICs-labelled education, and in non-labelled programmes and trainings [representation of either women or men not falling below 40% as a parity threshold] | Improve/introduce strategies and measures to increase participation of women in education programmes. Possible measures examples include: Active outreach to women (in case of women-dominated programmes - men), through tailored communication, and targeted marketing activities. Gender bias/ Diversity & inclusion, gendered education trainings, for education leads, advisory boards, expert groups. Inclusive education programmes design - taking into consideration, in relevance with the KICs business strategy, broader diversity dimensions, intersectionality. | EIT KICs have quality strategies and Action Plan in place, with sector-relevant KPIs and targets, to ensure gender smart approach to education. The Action Plan is monitored and annually reported on. Minimum 40% women and men in the EIT KICs -labelled education, and non-labelled programmes and trainings [KPI EITHE07.4], [KPI EITHE07.5], [KPI EITHE08.1] | EIT KICs - implementation and reporting (GMR); KPI reporting [KPI EITHE07.4/gender], [KPI EITHE07.5/gender], [KPI EITHE08.1/gender] EIT IES Gender Equality Lead, Education Lead: GMR assessment and steering exchange of knowledge and good practices OPS1: KPIs/ gender | Annually
|  | Strengthen and expand the EIT Community Girls Go Circular Programme | 100,000 girls trained by 2027 [KPI EITHE08.1] | EIT Community GGC - implementation EIT IES Cross-KIC Officer - monitoring and steering | Annually, target by 2027
| 5. Ensure that EIT KICs education programmes incorporate gender dimension | Introduce inclusive programmes design, and incorporation of gender dimension into education content, as award criterion in all EIT KICs Education Calls for Proposals, unless specified otherwise in the topic description. | EIT KICs Education Calls for Proposals include incorporation of gender dimension into education content, and inclusive programme design, as an award criterion, unless specified otherwise in the topic description. | EIT KICs - implementation and reporting EIT OPS1, External experts - Calls monitoring and evaluation | Annually, as of 2026
|  | Monitor and report on KIC impactful good practices and success stories on achieving gender-balance in education programmes, incorporation of gender dimension into education content, and inclusive education programme design- taking into consideration, in relevance with the KICs business strategy, broader diversity dimensions, intersectionality. | Annual EIT KICs Gender Mainstreaming Report includes quality information on the most successful examples of inclusive education programme design, and incorporation of gender dimension into education content. Key figures and selected good practices are featured on EIT Campus online. | EIT KICs - Implementation and reporting EIT IES Gender Equality Lead, IES Education Lead - GMR assessment and steering exchange of knowledge and good practices | Annually
Institutional transformation | 6. Ensure gender-balanced participation in EIT KICs decision making at all levels [representation of either women or men not falling below 40% as a parity threshold] | Improve/introduce strategies and measures to increase participation of women in the EIT KICs decision making. Possible measures include: Gender as a ranking criterion for candidates with equal scoring. Targets for % of women on short lists for all decision making positions. Gender-balanced, gender equality/gender bias trained selection panels. Use of tailored communication and marketing channels | Minimum 40% women and men in the EIT KICs decision making | EIT KICs-implementation and reporting EIT OPS1 - monitoring | Annually
|  | EIT incentivizes increasing participation of women in EIT KICs decision-making. | EIT maintains a gender equality KPI for KIC governance and management to ensure representation of underrepresented gender at all levels. | EIT HoU Supervision & Monitoring, EIT Management, supported by EIT GB | Annually
| 7. Ensure inclusive, empowering working environment for all | Improve Gender Equality Plans (GEPs), including strategies and measures to ensure inclusive, empowering environment for all. GEP aspects to reflect on include, but are not limited to: Incorporation of gender dimension into EIT KIC Strategic and Planning documents, and monitoring processes, in all areas of operations, including innovation, education, business creation & acceleration programmes. Awareness raising and capacity building, including annual diversity & inclusion/ unconscious bias/ anti-harassment/anti-discrimination/gender mainstreaming training for staff & decision-makers. Flexible working arrangements, child-care services, and other measures to support staff in combining professional and carrying roles. Monitoring and combating gender pay gap. | EIT KICs have published on their websites quality Gender Equality Plans, with SMART objectives, KPIs, and targets. The GEPs is annually monitored and reported on. Quality sex/gender disaggregated data is collected for all programmes. | EIT KICs - implementation and reporting EIT IES Gender Equality Lead - GMR assessment and steering exchange of knowledge and good practices | Annually
Strategic partnerships for gender equality | 8. Build impactful partnerships for gender equality in innovation and entrepreneurships in all EIT Community sectors by 2027 | Expend cooperation with the EUIPO on women IP rights, including awareness raising, and IP trainings for women entrepreneurs and innovators from the EIT Community. | Minimum 300 women entrepreneurs and innovators from the EIT Community attended EUIPO workshops/trainings on IP rights. | EIT KICs - coopeartion with EUIPO on IP trainings/awareness raising EIT IES, Gender Equality Lead, Education Officer leading on the MoU with EUIPO - steering cooperation between the EIT KICs and EUIPO | Annually, target to be reached by 2027
|  | Continue cooperation with EIC on European Prize for Women Innovators. | European Prize for Women Innovators is implemented annually. | European Prize - C&E Unit | Annually
|  | EIT KICs build partnerships for gender equality in innovation and entrepreneurship with key organisations and networks across Europe. | Annual EIT KICs Gender Mainstreaming Report includes information on KIC partnerships for gender equality with key organisations and networks across Europe (partner organisations, cooperation frame, impact). | EIT KICs - monitoring and reporting (GMR) EIT IES Gender Equality Lead - GMR assessment, steering exchange of knowledge and good practices | Annually
Communication for diversity & inclusion | 9. Increase awareness of the EIT Community activities, results, and impact on gender equality, women entrepreneurship & leadership, in Europe and beyond | Organize impactful events and communication campaigns on women entrepreneurship and leadership, gender equality in innovation, including involvement of press and targeted social media campaigns | EIT KICs organize minimum 2 (per KIC/ per year) impactful events and/or communication campaigns on women entrepreneurship and leadership, gender equality in innovation. | EIT KICs - Implementation and reporting EIT C&E - implementation of EIT events/communication campaigns, monitoring and steering KICs communication | Annually
|  |  | EIT organises per year minimum 1 impactful event and/or communication campaign on women entrepreneurship and leadership, gender equality in innovation, including involvement of press and social media. | EIT C&E - implementation | Annually
|  | Incorporate women entrepreneurship & leadership/gendered innovation/ diversity & inclusion topics into key EIT and KICs events, by, for example: including thematic panel discussion; adding WEL/D&I questions for panelists; ensuring participation of WEL/D&I experts/ champions in speaking roles at key events; adding WEL/D&I speaking points to briefings for high level speakers. | Minimum 40% women on speakers lists and in panel discussions at all EIT and EIT KICs events. Briefings for all key events include speaking points on gender equality/ women entrepreneurship & leadership/ D&I. | EIT KICs - Implementation and reporting EIT C&E - implementation for EIT key events, monitoring and steering KICs communication | Annually
|  | Ensure gender bias free communication by, among others: gender-balanced speakers lists and panel discussions; inclusive communication (images and texts) | images and texts published by the EIT and KICs are in line with the rules of gender-sensitive, inclusive communication | EIT KICs - Implementation and reporting EIT C&E - implementation for EIT and monitoring and steering KICs communication | Annually

## 2nd overarching objective GEP
EIT Gender Equality Action Plan 2025-2027
2. ENSURING GENDER EQUALITY AT THE EIT, INCLUDING GENDER BALANCED REPRESENTATION IN EIT STAFF AND MANAGEMENT
Objective | Activities | Results Indicators | Responsible(s) | Timeline
1. Ensure gender-balanced participation among the EIT Staff, with a special focus on managerial positions. [Representation of either women or men not falling below 40 % as a parity threshold] | Maintain gender as a ranking criterion for candidates with equal scoring. | Minimum 40% women and men in the EIT Management. Minimum 40% women and men at all levels among the EIT Staff by 2027. | EIT Director HoU Administration | Annually
| Use tailored communication and marketing channels to reach out to women candidates with the EIT job offers, for Units/Sections when women are underrepresented. | EIT job offers for Units/Sections were women are underrepresented, include text encouraging women candidates to apply, and are disseminated via tailored communication and marketing channels effectively reaching women. | HoU Administration | Annually
| Ensure that EIT selection panels are gender-balanced and undergo unconscious bias training | EIT selection committees members have undergone diversity & inclusion, unconscious bias training. EIT selection committees are gender-balanced. | HoU Administration | Annually
2. Ensure relevant expertise and resources for gender mainstreaming within the EIT | Maintain the position of the EIT Gender Equality Lead, and include contribution to the implementation of the EIT GEP in annual objectives and performance mechanisms of selected EIT Staff, allocating relevant time and resources. | EIT has appointed Gender Equality Lead, with relevant expertise and time allocation to effectively coordinate and monitor the implementation of the EIT Gender Equality Plan, and lead the work on gender mainstreaming. Selected EIT Staff's annual objectives include contribution to the work on gender equality, and the implementation of the EIT Gender Equality Plan in respective areas. | EIT Director Heads of Departments Heads of Units | Annually
| Ensure incorporation of gender dimension into EIT Strategic and Planning documents, and monitoring processes. | EIT Strategic and Planning Documents, as well as Monitoring Processes, incorporated gender dimension. | EIT Director, Heads of Departments, Heads of Units EIT Gender Equality Lead/external gender expert - content support | Annually
| Organize a gender mainstreaming workshop by 2027. | EIT Management and Staff have completed gender mainstreaming workshop. | HoU Administration: organisation, procurement, trainer selection. EIT Gender Equality Lead - content support | By 2027
3. Ensure inclusive, empowering working environment for all | Conduct Diversity & Inclusion Survey, in cooperation with the EUAN. | EIT Staff and Management participated in the EUAN D&I Survey. | EIT Director, Heads of Departments, Heads of Units | Q1 2025
| Organise a diversity and inclusion/ gender equality/ anti-discrimination/ anti-harassment training by 2027. | EIT Staff and Management have completed D&I/gender equality/anti-harassment/anti-discrimination training. | HoU Administration: organisation, procurement, trainer selection. EIT Gender Equality Lead - content support. | By 2027
| Diversity & Inclusion, gender equality aspects are incorporated into onboarding sessions for new Staff. | New EIT Staff receive information on the EIT Gender Equality Policy and Action Plan as part of their onboarding. | HoU Administration - organisation EIT Gender Equality Lead - content support | Annually